## Start here
Defect register for residential aftercare
Fictional example. Dates and details illustrate the process.
Use one row per case. Keep the current next action in Register and add dated changes to History. Store photos and documents in your team's chosen location and record their references or links.
How to use the register
1. Choose one person to maintain the register and agree where the current file lives.
2. Assign a unique case reference when a report arrives. Keep that reference unchanged.
3. Record the home and location, then the responsible team, next action and deadline when known.
4. Add completion evidence when work is reported complete. Record the care team's review separately.
5. Keep previous decisions in History. If a closed case returns for review, record the reopening and earlier closure there before updating the current row.
6. Share a separate, relevant extract with owners or contractors. Check the contents before sending it.
Register columns
Case reference | Text; unique and stable
Development | Text
Home reference | Text; preserve leading zeros
Room and location | Text
Date reported | Date
Defect description | Wrapped text
Photo references | Text/links to team-controlled files
Current stage | Suggested list below; worksheet-specific
Responsible team | Text
Next action | Text
Team-set deadline | Date; set by the care team
Visit date and time | Text
Work completed on | Date, if work occurred
Completion evidence | Text/links
Review outcome | Wrapped text; explain the actual decision
Reviewed by | Text
Reviewed on | Date
Closed on | Date, when the care team closes the case
Leave unknown dates empty.
Suggested stages
New | New means received and awaiting review.
Under review | Under review includes information requests and assessment.
Work arranged | Work arranged records an agreed next action or visit.
Ready for review | Ready for review means completion has been reported to the care team.
Closed | Closed means the team recorded an outcome; read Review outcome to understand it.
For a reopening, use Under review and preserve the previous decision in History.
History
Add a dated row when the next action, a date or the outcome changes. History can be edited, so it does not create an immutable record.
This is a standalone template. Its fields and stages are worksheet conventions and do not describe a Toveta import format or its application status labels.

## Register
Case reference | Development | Home reference | Room and location | Date reported | Defect description | Photo references | Current stage | Responsible team | Next action | Team-set deadline | Visit date and time | Work completed on | Completion evidence | Review outcome | Reviewed by | Reviewed on | Closed on
D-2026-014 | Example development | Apartment 12 | Kitchen, floor tile beside the doorway | 2026-09-14 | A crack runs across the floor tile beside the kitchen doorway. I noticed it on 14 September 2026. | D-2026-014-location.jpg; D-2026-014-detail.jpg | Closed | Tiling team | No further action recorded | 2026-09-24 | 22 Sep 2026, 09:00–11:00 | 2026-09-22 | Replacement tile fitted; D-2026-014-completed.jpg | Finished area checked against the original report; case closed. | Customer care team | 2026-09-24 | 2026-09-24

## History
Case reference | Date | Recorded by | Update | Next action
D-2026-014 | 2026-09-14 | Homeowner | Description and two photos received. | Review the report.
D-2026-014 | 2026-09-15 | Customer care team | Reference assigned; report reviewed; deadline set to 24 September; work assigned to tiling team. | Agree a visit.
D-2026-014 | 2026-09-18 | Customer care team | Visit agreed for 22 September, 09:00–11:00. | Carry out the work.
D-2026-014 | 2026-09-22 | Tiling team | Replacement tile fitted; completion photo provided. | Customer care review.
D-2026-014 | 2026-09-24 | Customer care team | Finished area checked; case closed; owner informed. | No further action recorded.